## Allocations
COMP322 Human Computer Interaction, Project allocations
Second semester 2025/26 ¦ Instructor: Dr Hisham Ihshaish ¦ Issued: Wednesday 6 May 2026
Each group has been allocated a specific system with a defined scope. Where many teams chose the same category, the concrete instance has been varied so no two teams analyse the same system. If your allocated service is not named below as a single product (e.g. e-government, NGO partner, campus event service), your first task is to LOCATE the live service yourselves: search, confirm the official URL or app store listing, and record it in the team-and-topic section of your Phase 1 report. The supporting templates (heuristics quick-reference, evaluation log, severity scale, persona template) are in the printable Word document distributed with this workbook. Read 'Distinct instances', 'Revised timeline', and 'What to do this week' before you start.
Group | Members | Stated preferences | Allocated category | Allocated system / app | Source: provided URL or self-locate? | Evaluation breadth (heuristic eval) | Redesign scope (specific user journeys) | Distinct from | Notes
Group 1 | Zaki Meslih (1230149); Zaid Qamhieh (1230206); Kyse Alqoran (1230966) | 1, 7, 9 | A, University services | Messaging app (WhatsApp or local equivalent) | Self-locate via the Birzeit website (ritaj.birzeit.edu). Confirm the URL of the registration sub-area in your report. | Walk the wider Ritaj registration experience for the heuristic evaluation, including adjacent screens a student would naturally hit while registering. | Redesign these flows: (1) searching for a course and viewing prerequisites; (2) adding a course to the registration cart; (3) confirming registration and resolving conflicts (time clash, capacity full). | Other Ritaj teams: grades (G8), schedule (G11). Do not work on grade or timetable screens.
Group 2 | Mays Al-Reem Hroub (1220081); Amro Al Deek (1221642); Hala Sulaiman (1202997); Mohammed Aljamal (1220378) | 10, 5, 6 | D, Custom topic (approved) | Bab idDeir gallery website | Provided in your proposal: babiddeir.ps. Confirm it still resolves and that key screens are reachable. | Evaluate the public website end to end for heuristics (browsing exhibitions, artist pages, shop, contact). | Redesign these flows: (1) discovering exhibitions and artworks (browse + filter); (2) viewing artwork detail and provenance; (3) adding to cart and completing checkout. | Unique to this team. | Confirm an interview slot with at least one Bab idDeir staff member by 12 May.
Group 3 | Cileen Antari (1220944); Deema Khalifah (1221619); Lara Shaltaf (1220063) | 6, 5 | B, Local digital services | Arab Bank Palestine, Arabi Mobile app | Self-locate via Google Play / App Store ('Arabi Mobile'). Record the app version in your report. | Evaluate the main authenticated areas of the app for heuristics (dashboard, transfers, statements, settings). | Redesign these flows: (1) first-time login and biometric setup; (2) local fund transfer to another Arab Bank account; (3) viewing and downloading an account statement. | Bank of Palestine is allocated to G13. Use Arab Bank Palestine specifically; do not analyse Bank of Palestine screens. | If no team member holds an account, observe a willing relative; do not record credentials.
Group 4 | Qossay Badaha (1210469); Nour Samhan (1211023); Aya Abdalkarim (1220020); Malak Abu Jarada (1221890) | 1, 6, 7 | B, Local digital services | Shini GO (food delivery) | Self-locate via Google Play / App Store. Record app version. | Evaluate the main customer-facing areas for heuristics (browse, restaurant page, cart, checkout, order tracking, order history). | Redesign these flows: (1) searching restaurants and filtering by cuisine and delivery time; (2) building an order with customisations; (3) tracking an order from placement to delivery. | Wheels (G12) is the ride-hailing instance; do not include ride-hailing flows.
Group 5 | Hanan Naji (1220651); Rahaf Badwan (1220654); Alaa Tanineh (1221601); Ayah Sarama (1221615) | 1, 2, 7 | A, University services | Birzeit library catalogue and e-resources | Self-locate via library.birzeit.edu. Confirm the catalogue URL and one or two e-resource entry points in your report. | Evaluate the catalogue search experience and the e-resource access path for heuristics. | Redesign these flows: (1) known-item search; (2) filtered exploratory search by subject, language, and availability; (3) reserving or accessing an e-resource off-campus. | Only library-allocated team.
Group 6 | Ru'aa Diab (1223056); Amal Alwahidi (1213085); Aseel Khatib (1221726) | 2, 7, 6 | C, Community needs | Carpool / commute-match service for Birzeit commuters | Self-locate. Survey what currently exists (informal WhatsApp groups, Facebook groups, any apps used in the West Bank). If nothing exists, document that, your redesign becomes a green-field design grounded in interview data. | Evaluate at least one existing tool that commuters currently use (formal app or informal group) for heuristics, even if imperfect, to ground your redesign. | Redesign / design these flows: (1) finding a recurring carpool match for the daily commute; (2) coordinating timing and contact with a verified driver; (3) cancelling or changing a commute booking. | G14's allocation is Palestine TechnoPark room booking. Do not include room-booking flows. | Several class members are commuters. Recruit interview participants from inside the cohort plus 1-2 outside it.
Group 7 | Osama Manassra (1203378); Sara Ahmad (1221786); Eman Ladadwah (1220719); Donia Assi (1222382) | 4, 9 | B, Local digital services | Palestinian Ministry of Interior, civil-affairs e-services | Self-locate. Search for the official ministry e-services portal, confirm the URL, and note which flows are public-facing. | Evaluate the public-facing portal end to end for heuristics (landing page, service catalogue, application start, status check). | Redesign these flows: (1) locating and starting an application for a civil document (e.g. ID renewal or birth certificate); (2) uploading required attachments and submitting; (3) tracking application status and collecting the result. | Unique allocation. | Restrict redesign to public-facing portal flows; do not redesign internal admin screens.
Group 8 | Mouath Masalmah (1220179); Yazan Suliman (1221961); Mustafa Alayasa (1221015); Ramzi Abu Falah (1230594) | 1, 6 | A, University services | Birzeit Ritaj portal, grades and academic record | Self-locate via ritaj.birzeit.edu. Confirm the URL of the grades and academic-record sub-areas. | Walk the grades and academic-record areas widely for heuristics, including adjacent screens (course details, transcript, holds). | Redesign these flows: (1) viewing the current semester's grades as they are published; (2) inspecting the cumulative record (GPA, credit hours by year); (3) spotting and querying a discrepancy with a course mark. | Other Ritaj teams: schedule (G11). Do not work on registration or timetable screens.
Group 9 | Shahd Rimawi (1220221); Hadil Joaidee (1221856); Rand Tabakhna (1222845) | 2, 3, 7 | A, University services | The Work Factory Ramallah, event listings | Self-locate via The Work Factory Ramallah website or social channels. Confirm the URL of their events or calendar listings interface in your report. | Evaluate The Work Factory Ramallah's event listings interface for heuristics (events page, event detail, booking or RSVP flow). | Redesign these flows: (1) discovering upcoming events and workshops at The Work Factory; (2) registering or reserving a place at an event; (3) receiving a confirmation and getting directions on the day. | G14's allocation is Palestine TechnoPark room booking. Do not include room-booking flows.
Group 10 (merged) | Ahmad Butmeh (1213413); Shahd Ghanem (1211873); Julia Duaibes (1222428); Mohammad Tawafshah (1220740) | G10: 3, 7, 9 ¦ G16: 5, 6, 1 | C, Community needs | Local NGO digital service (partner to be confirmed) | Self-locate. Bring two candidate NGO partners to the next session; instructor confirms one and ensures distinct partner from G15. | Once partner is confirmed, evaluate the NGO's public website / form flow end to end for heuristics. | Redesign these flows: (1) the NGO's primary public flow (e.g. enquiry or application for support); (2) volunteer or donor onboarding; (3) status check / follow-up. | G15 is the other NGO team; partner organisations will be different. | PENDING INSTRUCTOR APPROVAL: original Groups 10 and 16 each had 2 members, below the minimum of 3. They have been merged into a 4-member team. Confirm in the next session.
Group 11 | Jana Abdelmajeed (1230593); Ghaydaa Mallah (1230620); Lana Habboub (1242652); Shahd Othman (1243972) | 1, 2, 7 | A, University services | Birzeit Ritaj portal, schedule and timetable | Self-locate via ritaj.birzeit.edu. Confirm the URL of the timetable sub-area. | Walk the timetable area widely for heuristics, including how it appears on a phone browser. | Redesign these flows: (1) viewing the current semester's timetable on a phone; (2) spotting and resolving a clash before add/drop; (3) exporting the timetable to a personal calendar. | Other Ritaj teams: grades (G8). Do not work on registration or grade screens.
Group 12 | Alaa Haj Ali (1221192); Istabraq Asaid (1200518); Mohammed Ghusni (1210027) | 1, 6, 3 | B, Local digital services | Wheels (ride-hailing) | Self-locate via Google Play / App Store. Record app version. | Evaluate the main rider-facing areas for heuristics (booking, in-ride, history, payments). | Redesign these flows: (1) booking a ride from current location; (2) selecting ride type and confirming price; (3) tracking the driver, in-ride communication, rating after drop-off. | Shini GO (G4) is the food-delivery instance; do not include food-delivery flows.
Group 13 | Deema Abu Nimeh (1220002); Aseel Abdel Haq (1221024); Anas Anas Sayed Ahmad (1221020); Bahaa Bani Shamsaa (1220252) | 6, 1, 5 | B, Local digital services | Bank of Palestine, BOP mobile app | Self-locate via Google Play / App Store ('BOP Mobile'). Record app version. | Evaluate main authenticated areas for heuristics (dashboard, transfers, bills, settings). | Redesign these flows: (1) login and biometric setup; (2) local fund transfer to another BOP account; (3) paying a utility bill or topping up a wallet. | Arab Bank Palestine is allocated to G3. Use BOP specifically; do not analyse Arab Bank screens.
Group 14 | Basel Najjar (1220073); Mohammad Shoman (1212322); Issam Abdalkarim (1211821); Ahmad Abunajeeb (1202953) | (none submitted) | A, University services | Palestine TechnoPark room-booking system | Self-locate via the Palestine TechnoPark website (technopark.ps) or contact them directly. Confirm the URL of their room or space booking interface in your report. | Evaluate the TechnoPark booking interface for heuristics, including search, booking confirmation, and cancellation screens. | Redesign these flows: (1) finding an available meeting or working space at the TechnoPark within a time window; (2) booking the space and notifying team members; (3) cancelling or shortening a booking. | G9's allocation is The Work Factory Ramallah event listings. Do not include event listing flows. | Submit a contribution-statement plan in the Phase 1 cover so working arrangements are clear.
Group 15 | Nouraldin Aborahma (1243974); Abdalrahman Hussein (1220699); Nael Alhaj (1232664); Amir Kadadha (1221147) | 3, 9, 1 | C, Community needs | Local NGO digital service (partner to be confirmed) | Self-locate. Bring two candidate NGO partners to the next session; instructor confirms one and ensures distinct from G10. | Once partner is confirmed, evaluate the NGO's public website / form flow end to end for heuristics. | Redesign these flows: (1) primary public flow; (2) volunteer or beneficiary onboarding; (3) status / follow-up. | G10 (merged) is the other NGO team; partner organisations will be different.

## Distinct instances
Distinct instances, how oversubscribed categories were split
Each shared category was varied so no two teams analyse the same concrete system
Where many teams listed the same project number, the category was kept but the concrete instance differed for each team. Use this sheet to confirm what your team should and should not include in its scope.
Category | Concrete instance | Allocated to | User-journey angle | Notes
Project 1, Ritaj (oversubscribed: 9 teams chose it) | Ritaj, course registration | Group 1 | Search, add to cart, confirm; conflict resolution. | Largest sub-area.
Project 1, Ritaj | Ritaj, grades and academic record | Group 8 | Current grades, cumulative record, querying a mark.
Project 1, Ritaj | Ritaj, schedule and timetable | Group 11 | Mobile timetable, clash resolution, calendar export.
Project 2, Library | Library catalogue and e-resources | Group 5 | Known-item search, filtered exploratory search, off-campus access. | Single team in this category.
Project 3, Campus services (oversubscribed: 5 teams) | The Work Factory Ramallah, event listings | Group 9 | Discover, subscribe, day-of reminder.
Project 3, Campus services | Palestine TechnoPark, Palestine TechnoPark room booking | Group 14 | Find free room, book and invite, cancel.
Project 4, e-government | MoI civil-affairs e-services | Group 7 | Public-facing portal flows only. | Single team in this category.
Project 5, Bank app (oversubscribed: 4 teams) | Bank of Palestine, BOP mobile | Group 13 | Login, transfer, bill payment.
Project 5, Bank app | Arab Bank Palestine, Arabi Mobile | Group 3 | Login, transfer, statement download.
Project 6, Food / ride (oversubscribed: 8 teams) | Shini GO (food delivery) | Group 4 | Restaurant search, order build, order tracking.
Project 6, Food / ride | Wheels (ride-hailing) | Group 12 | Book, confirm, track, rate.
Project 7, Commuter students (oversubscribed: 7 teams) | Carpool / route matching for commuters | Group 6 | Match, coordinate, change/cancel. | Single team angle.
Project 9, NGO / small business | NGO partner #1 (TBC at next session) | Group 10 (merged) | Public flow, onboarding, status. | Different NGO from G15.
Project 9, NGO / small business | NGO partner #2 (TBC at next session) | Group 15 | Public flow, onboarding, status. | Different NGO from G10.
Project 10, Custom (approved) | Bab idDeir gallery (babiddeir.ps) | Group 2 | Discover, view, checkout. | Approved custom proposal.
Project 8 (disability tool): not allocated this term, no team selected it. Removed from the project menu.

## Revised timeline
Revised timeline (adjusted for the 5 May allocation announcement)
Phase 1 brought forward to Wednesday 20 May (15 days from announcement). Downstream phases re-spaced.
The original Phase 1 window (22 April brief, 13 May due) was 21 days. Allocations were issued tonight (Tuesday 5 May). Phase 1 has been set to Wednesday 20 May, giving 15 days. This is shorter than the original 21-day window but workable: the heuristic evaluation can begin immediately, and interview recruitment can run in parallel. Phase 2 and Phase 3 have moved by one to two weeks accordingly. Quiz and final exam dates are unchanged.
Milestone | Original date | Revised date | Notes
Allocations announced | n/a | Tuesday 5 May | This workbook + announcement issued.
Topic confirmation in class | Mon 27 April | Next class session (w/c 6 May) | Bring questions about your allocation. Custom topics confirmed.
Individual assignment due | Mon 11 May | Sunday 10 May | Heuristic evaluation of any public app NOT your team's project.
Phase 1 (Research and requirements) due | Wed 13 May | Wednesday 20 May | End of day. Single team report 5-7 pages plus appendix.
In-class quiz | Last week of May | Last week of May (unchanged) | Date confirmed in class one session in advance.
Phase 2 (Design and prototype) due | Wed 3 June | Wednesday 10 June | End of day. Design rationale, wireframes, interactive prototype.
Phase 3 (Evaluation and revision) due | Wed 17 June | Wednesday 24 June | End of day. Written deliverable; defended at the final presentation.
Final presentations | 20-24 June | Final teaching week (last week of June, slots TBC) | 12 minutes presentation + 5 minutes Q&A. Slide deck due 24 hours in advance.
Final exam | University-set | University-set (unchanged) | Covers all course material.

## What to do this week
What to do this week, Phase 1 step-by-step
Eight steps in order. Do them in sequence; do not skip ahead.
Phase 1 is about understanding users, not designing solutions. By Wednesday 20 May you must submit a 5-7 page report containing a heuristic evaluation, a small set of exploratory interviews, two personas, three scenarios, and 5-7 measurable usability requirements. Work in this order: you cannot write a persona before you have done interviews, and you cannot write requirements until you have personas. All four supporting templates are in the printable Word document distributed with this workbook.
Step | Activity | Who in the team | By when | Output
1 | Confirm your allocated system. If self-locate, find the official URL or app listing and record it. Sign up for any account you need (use a throwaway email if appropriate). | Whole team | Sat 9 May | URL or app store listing recorded; everyone has access.
2 | Write a half-page scope statement: copy your three user journeys from your allocation row, plus a one-paragraph justification of why the problem matters. Bring it to the next class for the instructor to sight. | Whole team | Next class session (w/c 6 May) | Half-page scope statement.
3 | Read the 'Heuristics quick-reference' and 'Severity rating reference' pages of the printable templates document. Each member skims the reference until you all agree on what each heuristic means. | Each member individually | Saturday 9 May | Confidence in the 10 heuristics.
4 | Conduct the heuristic evaluation. Each team member walks the system independently and logs at least 10 violations using the 'Heuristic evaluation log' template. Then meet, deduplicate, agree severities. Aim for 10-20 unique violations team-wide. | Each member individually, then team consolidation | Tuesday 12 May | Filled-in evaluation log; one paragraph summarising dominant problem patterns.
5 | Recruit interview participants. You need a minimum of 2, target 3-4. Real users of the system, not your roommates. Use the consent form from Appendix C of the project specification. | Whole team (split contacts) | Wednesday 13 May | Confirmed slots booked, consent forms ready.
6 | Conduct the interviews. Use the guide in Appendix B of the project specification as a starting point and adapt to your topic. 20-45 minutes each. Two team members present where possible: one leads, one takes notes. | Pairs of members | Monday 18 May | Notes within 24 hours of each interview, signed consent on file.
7 | Synthesise into personas (2) and scenarios (3). Use the persona template in the printable templates document. Personas come from interview data, not imagination. Scenarios are short narratives showing how each persona uses the redesigned system. | Whole team | Tuesday 19 May | Two personas, three scenarios.
8 | Write 5-7 measurable usability requirements. Each must be a measurable target (numbers, time, error rates) mapped to one of the six ISO 9241-11 usability goals. Then assemble the report and submit. | Whole team | Wednesday 20 May (end of day) | Phase 1 report submitted.

## Notes for instructor
Notes for instructor, flagged decisions and pending items
Items needing your confirmation in the next session
Internal sheet. Hide before distributing if you wish.
Item | Issue | Recommended action
Group 10 + Group 16 merger | Each had only 2 members (below the 3-minimum). Merged into a single Group 10 of 4 (Ahmad B, Shahd G, Julia, Mohammad T) and allocated NGO project, partner TBC. | Confirm the merger in the next session. If a student objects, fall back to a 2+2 split allocating both teams the NGO project with different partners.
Group 14, no preferences submitted | No preferences were filled in. Allocated to Palestine TechnoPark room-booking (project 3 sub-area). | Mention briefly in class that contribution and preference submission matters; they have a fair allocation regardless.
Group 15 + Group 10, both NGOs | Both teams allocated project 9. Need distinct NGO partners. | Ask each team to bring two candidate partners to the next session; you confirm one per team to avoid clashes.
Project 8 (disability tool) dropped | Zero teams selected it. | Acknowledge in announcement; mention it can return next term as a final-year project topic.
Phase 1 deadline shifted to Wed 20 May | 15 days from announcement. Tighter than original 21 but workable: heuristic evaluation can begin immediately; recruitment runs in parallel. | Mention rationale (allocation came late) so students see the adjustment is principled.
Phase 2 deadline shifted to Wed 10 June | Was 3 June. 21 days for Phase 2. | Confirm timing in next session.
Phase 3 deadline shifted to Wed 24 June | Was 17 June. 14 days for Phase 3. | Confirm; final presentations follow in the last teaching week.
Final presentation slot | Original window 20-24 June moved into final teaching week (last week of June). | Confirm exact slot allocation in the session two weeks before. Slide deck due 24 hours in advance still applies.
Shini GO and Wheels as Project 6 instances | Listed in the distinct-instances sheet as available but not allocated this term (only two teams ended up in the food/ride category after distribution). | No action needed; flagged for future-term reuse.
Quiz date | Last week of May, unchanged. | Confirm the exact date one session in advance, per the spec.